## V1
SHOW CODE ¦ PROJECT CODE NAME ¦ PRODUCTION COMPANY
WIP POST PRODUCTION SCHEDULE ¦ DETAILED VIEW ¦ DATE¦ VERSION #X ¦ X x X min eps ¦ VFX X weeks | [18 empty] | DIRECTOR 1 | DIRECTOR 2 | DIRECTOR 3 | EDITOR 1 (LAURA MORROD) | EDITOR 2 (TOM WHITE) | EDITOR 3 (CAT GREGORY) | 1st AE#1 (KEIR GREATOREX) // EDIN) | 1st AE #1 (TBC // LON) | 1st AE# 2 (TBC) | 2nd AE#3 (TBC) | EDIT TRAINEE (TBC) | GRADE PENCILS (GOLDCREST) | MIX PENCILS (BOOM) | PULSE
| Shoot dates per Prelim One-liner 5 29/10/2021 | PREP | TEST VOL. | SHOOT | POST | DIRECTOR 1 NAME | VFX wks | DIRECTOR 2 NAME | VFX wks | DIRECTOR 1 NAME | VFX wks | DIRECTOR 3 NAME | VFX wks | DIRECTOR 2 NAME | VFX wks | DIRECTOR 3 NAME | VFX wks
[6 empty] | EDITOR 1 NAME |  | EDITOR 2 NAME |  | EDITOR 1 NAME |  | EDITOR 3 NAME |  | EDITOR 2 NAME |  | EDITOR 3 NAME
[6 empty] | DOP 1 NAME |  | DOP TBC |  | DOP 1 NAME |  | DOP 1 NEVILLE KIDD |  | DOP TBC |  | DOP 1 NEVILLE KIDD
[6 empty] | EP 101 // Block 1 |  | EP 102 // Block 2 |  | EP 103 // Block 1 |  | EP 104 // Block 3 |  | EP 105 // Block 2 |  | EP 106 // Block 3
2021-04-26 | [17 empty] | 2021-04-26
2021-05-03 | [17 empty] | 2021-05-03
2021-05-10 | [17 empty] | 2021-05-10
2021-05-17 | [17 empty] | 2021-05-17
2021-05-24 | [17 empty] | 2021-05-24
2021-05-31 | [17 empty] | 2021-05-31
2021-06-07 | PREP START | 1 | [15 empty] | 2021-06-07
2021-06-14 |  | 2 | [15 empty] | 2021-06-14
2021-06-21 |  | 3 | [15 empty] | 2021-06-21
2021-06-28 |  | 4 | [15 empty] | 2021-06-28
2021-07-05 |  | 5 | [15 empty] | 2021-07-05
2021-07-12 |  | 6 | [15 empty] | 2021-07-12
2021-07-19 |  | 7 | [15 empty] | 2021-07-19
2021-07-26 |  | 8 | [15 empty] | 2021-07-26
2021-08-02 |  | 9 | [15 empty] | 2021-08-02
2021-08-09 |  | 10 | [15 empty] | 2021-08-09
2021-08-16 |  | 11 | [15 empty] | 2021-08-16
2021-08-23 |  | 12 | [15 empty] | 2021-08-23
2021-08-30 |  | 13 |  | -12 | [13 empty] | 2021-08-30 | HC
2021-09-06 | STUDIO AVAIL / SET BUILD | 14 |  | -11 | [13 empty] | 2021-09-06 | HC
2021-09-13 |  | 15 |  | -10 | [13 empty] | 2021-09-13 | HC
2021-09-20 |  | 16 |  | -9 | [13 empty] | 2021-09-20 | HC | JJ
2021-09-27 |  | 17 |  | -8 | [13 empty] | 2021-09-27 | HC | JJ
2021-10-04 |  | 18 |  | -7 | [13 empty] | 2021-10-04 | HC | JJ
2021-10-11 |  | 19 |  | -6 | [13 empty] | 2021-10-11 | HC | JJ
2021-10-18 |  | 20 |  | -5 | [13 empty] | 2021-10-18 | HC | JJ
2021-10-25 |  | 21 |  | -4 | [13 empty] | 2021-10-25 | HC | JJ
2021-11-01 |  | 22 |  | -3 | [13 empty] | 2021-11-01 | HC | JJ | AS |  |  |  | 1 |  | 1
2021-11-08 | EDITOR 1 START | 23 |  | -2 | [13 empty] | 2021-11-08 | HC | JJ | AS | 1 |  |  | 2 |  | 2 | 1 | 1
2001-01-01 |  | 24 |  | -1 | [13 empty] | 2021-11-15
2001-01-02 | [17 empty] | 2021-11-16
2001-01-03 | [17 empty] | 2021-11-17
2001-01-04 | SHOOT STARTS |  |  |  |  | 8pt / 9pt / 12pt / 13 / 14pt / 15 / 17 / 18pt / 20 / 22 | [11 empty] | 2021-11-18
2001-01-05 | [5 empty] | 23pt / 24pt / 25 / 26 | [11 empty] | 2021-11-19
2001-01-06 | [17 empty] | 2021-11-20
2001-01-07 | [17 empty] | 2021-11-21
2001-01-08 |  |  | 1 | 1 |  | 7 / 8pt | [11 empty] | 2021-11-22 | HC | JJ | AS | 1 |  |  | 1 |  | 1 | 1 | 2
2001-01-09 | [5 empty] | 65 / 69 / 73pt / (74 RH) |  |  |  | 62 / 67 | [7 empty] | 2021-11-23
2001-01-10 | [5 empty] | 66pt / 67 / 68 / 74 | [11 empty] | 2021-11-24
2001-01-11 | [9 empty] | 11 | [7 empty] | 2021-11-25
2001-01-12 | [7 empty] | 23 / 35 / 36 / 37 | [9 empty] | 2021-11-26
2001-01-13 | [17 empty] | 2021-11-27
2001-01-14 | [17 empty] | 2021-11-28
2001-01-15 |  |  | 2 | 2 |  |  |  | 1 / 2(pt1) | [9 empty] | 2021-11-29 | HC | JJ | AS | 2 | 1 |  | 2 |  | 2 | 2 | 3
2001-01-16 | EDITOR 2 START | [6 empty] | 60 | [9 empty] | 2021-11-30
2001-01-17 | [7 empty] | 61 / 62 / 73 / 77 | [9 empty] | 2021-12-01
2001-01-18 | [7 empty] | 3 / 22 / 24(pt1) / 38 / 49(pt1) / 51 | [9 empty] | 2021-12-02
2001-01-19 | [7 empty] | 34 / 39 / 75 / 76 / 78 |  | 2pt / 3 | [7 empty] | 2021-12-03
2001-01-20 | [17 empty] | 2021-12-04
2001-01-21 | [17 empty] | 2021-12-05
2001-01-22 |  |  | 3 | 3 | [5 empty] | 68pt / 69 | [7 empty] | 2021-12-06 | HC | JJ | AS | 3 | 2 |  | 3 |  | 3 | 3 | 4
2001-01-23 | [9 empty] | 46 / 47 | [7 empty] | 2021-12-07
2001-01-24 | [7 empty] | 52 |  |  |  | 16 | [5 empty] | 2021-12-08
2001-01-25 | [11 empty] | 08 / 13 |  |  |  | 51 |  | 2021-12-09
2001-01-26 | [11 empty] | 07 /11 | [5 empty] | 2021-12-10
2001-01-27 | [17 empty] | 2021-12-11
2001-01-28 | [17 empty] | 2021-12-12
2001-01-29 |  |  | 4 | 4 |  | 73pt |  |  |  | 22 / 23 / 24pt / 51 / 55 | [7 empty] | 2021-12-13 | HC | JJ | AS | 4 | 3 |  | 4 |  | 4 | 4 | 5
2001-01-30 | VOLUME AVAILABLE TO SHOOT |  |  |  |  | 58 |  |  |  | 4pt / 6pt / 6pt | [7 empty] | 2021-12-14
2001-01-31 | [5 empty] | 32pt / 32pt / 33pt / 33pt |  |  |  | 26pt / 28pt / 48pt | [7 empty] | 2021-12-15
2001-02-01 | [5 empty] | 50pt |  |  |  | 56pt |  | 42pt / 44 | [5 empty] | 2021-12-16
2001-02-02 | [9 empty] | 1pt / 2pt / 4pt / 5pt / 8pt / 10pt / 14pt / 15 / 21 |  | 3 |  | 63 / 64 |  |  |  | 2021-12-17
2001-02-03 | [17 empty] | 2021-12-18
2001-02-04 | [17 empty] | 2021-12-19
2001-02-05 | [17 empty] | 2021-12-20
2001-02-06 | [17 empty] | 2021-12-21
2001-02-07 | [17 empty] | 2021-12-22
2001-02-08 | [17 empty] | 2021-12-23
2001-02-09 | [17 empty] | 2021-12-24
2001-02-10 | [17 empty] | 2021-12-25
2001-02-11 | [17 empty] | 2021-12-26
2001-02-12 | Holiday Hiatus | [16 empty] | 2021-12-27
2001-02-13 | Holiday Hiatus | [16 empty] | 2021-12-28
2001-02-14 | Holiday Hiatus | [16 empty] | 2021-12-29
2001-02-15 | Holiday Hiatus | [16 empty] | 2021-12-30
2001-02-16 | Holiday Hiatus | [16 empty] | 2021-12-31
2001-02-17 | [17 empty] | 2022-01-01
2001-02-18 | [17 empty] | 2022-01-02
2001-02-19 |  |  | 6 | 6 |  | BANK HOLIDAY |  | BANK HOLIDAY |  | BANK HOLIDAY |  | BANK HOLIDAY |  | BANK HOLIDAY |  | BANK HOLIDAY |  | 2022-01-03 | HC | JJ | AS | 5 | 4 |  | 5 |  | 5 | 5 | 6 |  |  | 1
2001-02-20 | EDITOR 3 START |  |  |  |  | PREP DAY |  | PREP DAY |  | PREP DAY |  | PREP DAY |  | PREP DAY |  | PREP DAY |  | 2022-01-04
2001-02-21 | [5 empty] | PREP DAY |  | PREP DAY |  | PREP DAY |  | PREP DAY |  | PREP DAY |  | PREP DAY |  | 2022-01-05
2001-02-22 | [11 empty] | 9pt / 10 / 12 | [5 empty] | 2022-01-06
2001-02-23 | [11 empty] | 02 / 14 | [5 empty] | 2022-01-07
2001-02-24 | [11 empty] | 15 | [5 empty] | 2022-01-08
2001-02-25 | [17 empty] | 2022-01-09
2001-02-26 |  |  | 7 | 7 |  | 59 |  | 9 |  | 7pt | [7 empty] | 2022-01-10 | HC | JJ | AS | 6 | 5 |  | 6 |  | 6 | 6 | 7 |  |  | 2
2001-02-27 | [7 empty] | 4 / 9 / 10(pt2) / 10(pt3) / 25 / 43(pt1) |  |  |  | 39 | [5 empty] | 2022-01-11
2001-02-28 | [5 empty] | 50pt / 64pt |  | 6pt1 |  | 31pt / 56pt | [7 empty] | 2022-01-12
2001-03-01 | [7 empty] | 64 / 65 / 66 / 67 / 68 / 69 / 70 / 71 / 72 / 74pt1 | [9 empty] | 2022-01-13
2001-03-02 | [9 empty] | 24pt / 33B / 61 |  | 35 | [5 empty] | 2022-01-14
2001-03-03 | [17 empty] | 2022-01-15
2001-03-04 | [17 empty] | 2022-01-16
2001-03-05 |  |  | 8 | 8 | [5 empty] | 39 | [7 empty] | 2022-01-17 | HC | JJ | AS | 7 | 6 | 1 | 7 |  | 7 | 7 | 8 |  |  | 3
2001-03-06 | [5 empty] | 34 / 37 / 40pt / 42pt / 48pt | [11 empty] | 2022-01-18
2001-03-07 | [5 empty] | 39 / 41 / 53 / 54pt / 54pt | [11 empty] | 2022-01-19
2001-03-08 | [5 empty] | 23pt / 24pt / 47pt / 48pt / 52pt |  |  |  | 1pt / 2pt / 4pt / 5pt / 6pt / 8pt / ? | [7 empty] | 2022-01-20
2001-03-09 | [11 empty] | 32 |  | 4 / 5 / 6 / 9 |  |  |  | 2022-01-21
2001-03-10 | [17 empty] | 2022-01-22
2001-03-11 | [17 empty] | 2022-01-23
2001-03-12 |  |  | 9 | 9 | [5 empty] | 42 | [7 empty] | 2022-01-24 | HC | JJ | AS | 8 | 7 | 2 | 8 |  | 8 | 8 | 9 |  |  | 4
2001-03-13 | [9 empty] | 17 / 33 / 33C / 34 | [7 empty] | 2022-01-25
2001-03-14 | [9 empty] | 37pt / 45 | [7 empty] | 2022-01-26
2001-03-15 | [5 empty] | 38pt | [7 empty] | 7 / 10 / 12 |  |  |  | 2022-01-27
2001-03-16 | [9 empty] | 40 | [7 empty] | 2022-01-28
2001-03-17 | [13 empty] | 8 / 11 |  |  |  | 2022-01-29
2001-03-18 | [17 empty] | 2022-01-30
2001-03-19 |  |  | 10 | 10 |  | 35 / 36 / 38pt |  |  |  | 16 / 32 | [7 empty] | 2022-01-31 | HC | JJ | AS | 9 | 8 | 3 | 9 |  | 9 | 9 | 10 |  |  | 5
2001-03-20 | [5 empty] | 1 / 9pt / 42pt | [9 empty] | 46pt |  | 2022-02-01
2001-03-21 | [5 empty] | 2 |  | 10(pt1) / 63 / 74(pt2) | [9 empty] | 2022-02-02
2001-03-22 | [5 empty] | 3pt / 4pt / 5pt / 6pt | [11 empty] | 2022-02-03
2001-03-23 | [5 empty] | 3pt / 4pt / 5pt / 6pt | [11 empty] | 2022-02-04
2001-03-24 | [17 empty] | 2022-02-05
2001-03-25 | [17 empty] | 2022-02-06
2001-03-26 |  |  | 11 | 11 |  |  |  | 18 | [5 empty] | 45 |  |  |  | 2022-02-07 | HC | JJ | AS | 10 | 9 | 4 | 10 |  | 10 | 10 | 11 |  |  | 6
2001-03-27 | [5 empty] | 14pt |  | 49(pt2) / 50 | [9 empty] | 2022-02-08
2001-03-28 | [9 empty] | 38 | [7 empty] | 2022-02-09
2001-03-29 | [5 empty] | 50pt / 51 / 60 / 61 / 62 / 63pt / 63pt |  |  |  | 63pt | [7 empty] | 2022-02-10
2001-03-30 | [5 empty] | 64pt |  | 5 / 6(pt2) / 6(pt3) |  | 30 / 31pt | [7 empty] | 2022-02-11
2001-03-31 | [17 empty] | 2022-02-12
2001-04-01 | [17 empty] | 2022-02-13
2001-04-02 |  |  | 12 | 12 | [5 empty] | 7pt / 9 / 58pt | [7 empty] | 2022-02-14 | HC | JJ | AS | 11 | 10 | 5 | 11 |  | 11 | 11 | 12 |  |  | 7
2001-04-03 | [9 empty] | 58pt / 59 / 60 / 63pt / 66 | [7 empty] | 2022-02-15
2001-04-04 | [15 empty] | 16 |  | 2022-02-16
2001-04-05 | [15 empty] | 15 / 22 / 39pt / 41pt |  | 2022-02-17
2001-04-06 | [5 empty] | 16 | [11 empty] | 2022-02-18
2001-04-07 | [5 empty] | 18pt / 21 | [11 empty] | 2022-02-19
2001-04-08 | [17 empty] | 2022-02-20
2001-04-09 |  |  | 13 | 13 |  | 66pt |  | 13 / 15 / 16 / 18(pt1) |  | 52 | [7 empty] | 2022-02-21 | HC | JJ | AS | 12 | 11 | 6 | 12 |  | 12 | 12 | 13 |  |  | 8
2001-04-10 | [7 empty] | 11 / 12 | [9 empty] | 2022-02-22
2001-04-11 | [5 empty] | 55 / 72pt |  | 43(pt2) | [9 empty] | 2022-02-23
2001-04-12 | [5 empty] | 64pt / 72pt |  | 7(pt1) / 33 |  |  |  | 1 | [5 empty] | 2022-02-24
2001-04-13 | [5 empty] | 10 / 12pt |  | 42 / 46 / 47 /48 | [9 empty] | 2022-02-25
2001-04-14 | [17 empty] | 2022-02-26
2001-04-15 | [17 empty] | 2022-02-27
2001-04-16 |  |  | 14 | 14 |  | 28 / 29 |  |  |  | 49pt / 49pt / 65 | [7 empty] | 2022-02-28 | HC | JJ | AS | 13 | 12 | 7 | 13 |  | 13 | 13 | 14 |  |  | 9
2001-04-17 | [5 empty] | 30 / 31 | [7 empty] | 2(pt1) |  | 46pt |  | 2022-03-01
2001-04-18 | [13 empty] | 2(pt2) / 3 / 44 |  |  |  | 2022-03-02
2001-04-19 | [5 empty] | 43 / 44 / 45 / 46 / 47pt | [11 empty] | 2022-03-03
2001-04-20 | [7 empty] | 19 / 20 / 21 |  | 18pt / 20B / 37pt | [7 empty] | 2022-03-04
2001-04-21 | [17 empty] | 2022-03-05
2001-04-22 | [17 empty] | 2022-03-06
2001-04-23 |  |  | 15 | 15 | [7 empty] | 26 / 28 / 30 | [5 empty] | 2022-03-07 | HC | JJ | AS | 14 | 13 | 8 | 14 |  | 14 | 14 | 15 |  |  | 10
2001-04-24 | [5 empty] | 70pt / 71 | [11 empty] | 2022-03-08
2001-04-25 | [5 empty] | 72pt | [11 empty] | 2022-03-09
2001-04-26 | [11 empty] | 23 / 24 | [5 empty] | 2022-03-10
2001-04-27 | [11 empty] | 37 / 38 |  | 13 |  |  |  | 2022-03-11
2001-04-28 | [17 empty] | 2022-03-12
2001-04-29 | [17 empty] | 2022-03-13
2001-04-30 |  |  | 16 | 16 |  | 14(pt1) | [11 empty] | 2022-03-14 | HC | JJ | AS | 15 | 14 | 9 | 15 |  | 15 | 15 | 16 |  |  | 11
2001-05-01 | [7 empty] | 14(pt2) / 17 | [9 empty] | 2022-03-15
2001-05-02 | [5 empty] | 57 |  |  |  | 25 / 26pt / 64 | [7 empty] | 2022-03-16
2001-05-03 | [7 empty] | 57(pt2) / 58 / 59(pt1) |  | 38Apt |  |  |  | 15 / 16 |  |  |  | 2022-03-17
2001-05-04 | [9 empty] | 29 / 57 |  | 21 / 36 | [5 empty] | 2022-03-18
2001-05-05 | [7 empty] | 54 / 55 / 56 |  | 33A / 50pt / 53 / 54 | [7 empty] | 2022-03-19
2001-05-06 | [17 empty] | 2022-03-20
2001-05-07 |  |  | 17 | 17 |  | DIRECTOR CUT |  |  |  | DIRECTOR CUT |  | 17 / 19 / 20 / 22 / 25 / 34 | [5 empty] | 2022-03-21 | HC | JJ | AS | 16 | 15 | 10 | 16 |  | 16 | 16 | 17 |  |  | 12
2001-05-08 | [5 empty] | DIRECTOR CUT |  |  |  | DIRECTOR CUT |  | 31 / 33 | [5 empty] | 2022-03-22
2001-05-09 | [5 empty] | DIRECTOR CUT |  |  |  | DIRECTOR CUT |  |  |  | 39 / 54(pt1) / 54(pt2) / 54(pt3) / 54(pt4) / 54(pt5) / 55 |  |  |  | 2022-03-23
2001-05-10 | [5 empty] | DIRECTOR CUT |  |  |  | DIRECTOR CUT |  |  |  | 60 / 61 / 62 |  |  |  | 2022-03-24
2001-05-11 | [5 empty] | DIRECTOR CUT |  |  |  | DIRECTOR CUT |  |  |  | 23 / 24 / 72 / 73 |  |  |  | 2022-03-25
2001-05-12 | HMC to US 26/03/22 | [16 empty] | 2022-03-26
2001-05-13 | [17 empty] | 2022-03-27
2001-05-14 |  |  | 18 | 18 |  | DIRECTOR CUT (remote) |  |  |  | DIRECTOR CUT (remote) | [5 empty] | 1 / 7 / 8 / 11 |  | 2022-03-28 | HC | JJ | AS | 17 | 16 | 11 | 17 |  | 17 | 17 | 18 |  |  | 13
2001-05-15 | [5 empty] | DIRECTOR CUT (remote) |  |  |  | DIRECTOR CUT (remote) | [5 empty] | 12 / 17 / 19 / 21 |  | 2022-03-29
2001-05-16 | [5 empty] | DIRECTOR CUT (remote) |  |  |  | DIRECTOR CUT (remote) | [5 empty] | 2014-09-03 |  | 2022-03-30
2001-05-17 | [5 empty] | DIRECTOR CUT (remote) |  |  |  | DIRECTOR CUT (remote) | [5 empty] | 20 / 26 |  | 2022-03-31
2001-05-18 | [5 empty] | DIRECTOR CUT (remote) |  |  |  | DIRECTOR CUT (remote) |  |  |  | 22(pt2) / 27 |  | 30 |  | 2022-04-01
2001-05-19 | [17 empty] | 2022-04-02
2001-05-20 | [17 empty] | 2022-04-03
2001-05-21 |  |  | 19 | 19 |  | DIRECTOR CUT (remote) |  | 7(pt2) / 8 / 24(pt2) / 26 / 27 / 28 |  | DIRECTOR CUT (remote) | [7 empty] | 2022-04-04 |  | JJ | AS | 18 | 17 | 12 | 18 |  | 18 | 18 | 19 |  |  | 14
2001-05-22 | [5 empty] | DIRECTOR CUT (remote) |  | 29 / 30 / 31 / 32 / 40 / 41 |  | DIRECTOR CUT (remote) | [7 empty] | 2022-04-05
2001-05-23 | [5 empty] | DIRECTOR CUT (remote) |  | 43(pt3) / 44 / 45 / 53 / 59(pt2) |  | DIRECTOR CUT (remote) |  |  |  | 32 / 42 |  |  |  | 2022-04-06
2001-05-24 | [5 empty] | DIRECTOR CUT (remote) |  |  |  | DIRECTOR CUT (remote) |  | 18 / 43 |  | 22(pt1) / 65 |  |  |  | 2022-04-07
2001-05-25 | [5 empty] | DIRECTOR CUT (remote) |  |  |  | DIRECTOR CUT (remote) |  | 4 / 6pt |  | 1 |  | 38 |  | 2022-04-08
2001-05-26 | [17 empty] | 2022-04-09
2001-05-27 | HMC to UK 10/04 for 2 weeks |  |  |  |  | HMC travel to UK | [11 empty] | 2022-04-10
2001-05-28 |  |  | 20 | 20 |  | HMC arrive UK | [5 empty] | 45 / 46pt | [5 empty] | 2022-04-11 |  | JJ | AS | 19 | 18 | 13 | 19 |  | 19 | 19 | 20 |  |  | 15
2001-05-29 | [5 empty] | DIRECTOR CUT | [5 empty] | 46pt | [5 empty] | 2022-04-12
2001-05-30 | [5 empty] | DIRECTOR CUT | [7 empty] | 18 / 19 / 46 |  |  |  | 2022-04-13
2001-05-31 | [5 empty] | DIRECTOR CUT | [7 empty] | 66 / 68 / 76 |  |  |  | 2022-04-14
2001-06-01 | [5 empty] | Ep1 Directors Cut delivered to Producers | [9 empty] | 25 |  | 2022-04-15
2001-06-02 | [17 empty] | 2022-04-16
2001-06-03 | [17 empty] | 2022-04-17
2001-06-04 | Cut Zero - Directors Cut? |  | 21 | 21 |  |  |  | DIRECTOR CUT |  | 43 / 44 | [7 empty] | 2022-04-18 |  | JJ | AS | 20 | 19 | 14 | 20 |  | 20 | 20 | 21 |  |  | 16
2001-06-05 | [7 empty] | DIRECTOR CUT |  |  |  | 5 / 6pt / 29 | [5 empty] | 2022-04-19
2001-06-06 | [9 empty] | 68pt |  |  |  | 17 / 20 |  |  |  | 2022-04-20
2001-06-07 | [7 empty] | DIRECTOR CUT | [7 empty] | 39pt / 41pt |  | 2022-04-21
2001-06-08 | [7 empty] | DIRECTOR CUT | [7 empty] | 39pt / 41pt |  | 2022-04-22
2001-06-09 | [9 empty] | 18pt / 19 / 20 | [7 empty] | 2022-04-23
2001-06-10 | [17 empty] | 2022-04-24
2001-06-11 | LDD 25/04 |  | 22 | 22 |  |  |  | DIRECTOR CUT |  | 20A | [7 empty] | 2022-04-25 |  | JJ | AS | 21 | 20 | 15 | 21 |  | 21 | 21 | 22 |  |  | 17
2001-06-12 | HMC to US 26/04? | [6 empty] | DIRECTOR CUT |  | Assembly catch up |  | 27 |  |  |  | 44 / 48 / 54 |  | 2022-04-26
2001-06-13 | [9 empty] | Assembly catch up |  |  |  | 25 / 26 / 38 / 74 |  |  |  | 2022-04-27
2001-06-14 | [9 empty] | DIRECTOR CUT (remote) |  |  |  | 77 / 79 |  |  |  | 2022-04-28
2001-06-15 | [9 empty] | DIRECTOR CUT (remote) | [5 empty] | 2 / 18 |  | 2022-04-29
2001-06-16 | [17 empty] | 2022-04-30
2001-06-17 | [17 empty] | 2022-05-01
2001-06-18 |  |  | 23 | 23 | [5 empty] | DIRECTOR CUT (remote) |  |  |  | 35 / 36 / 37 |  |  |  | 2022-05-02 |  | JJ | AS | 22 | 21 | 16 | 22 |  | 22 | 22 | 23 |  |  | 18
2001-06-19 | [9 empty] | DIRECTOR CUT (remote) |  |  |  | 31 / 33 / 47 / 52 / 56 / 58 |  |  |  | 2022-05-03
2001-06-20 | [9 empty] | DIRECTOR CUT (remote) |  |  |  | 28 / 29 / 30 / 34 / 51 |  | 5 / 23 |  | 2022-05-04
2001-06-21 | [9 empty] | DIRECTOR CUT (remote) |  |  |  | 48 / 49 / 50 / 57 / 59 / 67 |  |  |  | 2022-05-05
2001-06-22 | [9 empty] | DIRECTOR CUT (remote) |  |  |  | 69 / 70 / 71 / 75 / 78 |  |  |  | 2022-05-06
2001-06-23 | [9 empty] | Ep 3 Directors Cut delivered to Producers | [5 empty] | 4 / 6 / 10 / 13 |  | 2022-05-07
2001-06-24 | [17 empty] | 2022-05-08
2001-06-25 |  |  | 24 | 24 |  | EXEC CUT |  | DIRECTOR CUT | [7 empty] | 24 / 27 |  | 2022-05-09 |  | JJ | AS | 23 | 22 | 17 | 23 |  | 23 | 23 | 24 |  |  | 19
2001-06-26 | [5 empty] | EXEC CUT |  | DIRECTOR CUT | [7 empty] | 28 |  | 2022-05-10
2001-06-27 | [5 empty] | EXEC CUT |  | DIRECTOR CUT | [7 empty] | 29 / 31 / 32 |  | 2022-05-11
2001-06-28 | [5 empty] | EXEC CUT |  | DIRECTOR CUT | [7 empty] | 35pt / 36 / 37pt / 42 |  | 2022-05-12
2001-06-29 | SHOOT WRAP |  |  |  |  | EXEC CUT |  | Ep 2 Directors Cut delivered to Producers | [7 empty] | 34 / 35pt / 37pt / 40 / 43 |  | 2022-05-13
2001-06-30 | [17 empty] | 2022-05-14
2001-07-01 | [17 empty] | 2022-05-15
2001-07-02 |  |  |  |  | 1 | EXEC CUT | [5 empty] | DIRECTOR CUT |  | DIRECTOR CUT |  |  |  | 2022-05-16 |  | JJ | AS | 1 | 1 | 1 | 24 | 1 | 1 | 1 | 25 |  |  | 20
2001-07-03 | [5 empty] | EXEC CUT | [5 empty] | DIRECTOR CUT |  | DIRECTOR CUT |  |  |  | 2022-05-17
2001-07-04 | [5 empty] | EXEC CUT | [5 empty] | DIRECTOR CUT |  | DIRECTOR CUT |  |  |  | 2022-05-18
2001-07-05 | [5 empty] | EXEC CUT | [5 empty] | DIRECTOR CUT |  | DIRECTOR CUT |  |  |  | 2022-05-19
2001-07-06 | [5 empty] | Cut 0.1 Delivered to AMZ | [5 empty] | DIRECTOR CUT |  | DIRECTOR CUT |  |  |  | 2022-05-20
2001-07-07 | [17 empty] | 2022-05-21
2001-07-08 | [17 empty] | 2022-05-22
2001-07-09 |  |  |  |  | 2 | AMAZON CUTS (4 WEEKS) |  | EXEC CUT |  |  |  | DIRECTOR CUT |  | DIRECTOR CUT |  |  |  | 2022-05-23 |  | JJ | AS | 2 | 2 | 2 |  | 2 | 2 | 2 |  |  |  | 21
2001-07-10 | [7 empty] | EXEC CUT |  |  |  | DIRECTOR CUT |  | DIRECTOR CUT |  |  |  | 2022-05-24
2001-07-11 | [7 empty] | EXEC CUT |  |  |  | DIRECTOR CUT |  | DIRECTOR CUT |  |  |  | 2022-05-25
2001-07-12 | [5 empty] | Cut 0.2 Delivered to AMZ EOD |  | EXEC CUT |  |  |  | DIRECTOR CUT |  | DIRECTOR CUT |  |  |  | 2022-05-26
2001-07-13 | [7 empty] | EXEC CUT |  |  |  | Ep 4 Directors Cut delivered to Producers |  | Ep 5 Directors Cut delivered to Producers |  |  |  | 2022-05-27
2001-07-14 | [17 empty] | 2022-05-28
2001-07-15 | [17 empty] | 2022-05-29
2001-07-16 |  |  |  |  | 3 |  |  | EXEC CUT |  | EXEC CUT | [5 empty] | DIRECTOR CUT |  | 2022-05-30 |  | JJ | AS | 3 | 3 | 3 |  | 3 | 3 | 3 |  |  |  | 22
2001-07-17 | [7 empty] | EXEC CUT |  | EXEC CUT | [5 empty] | DIRECTOR CUT |  | 2022-05-31
2001-07-18 | [5 empty] | Cut 1 Delivered to AMZ EOD |  | EXEC CUT |  | EXEC CUT | [5 empty] | DIRECTOR CUT |  | 2022-06-01
2001-07-19 | [7 empty] | EXEC CUT |  | EXEC CUT | [5 empty] | DIRECTOR CUT |  | 2022-06-02
2001-07-20 | [7 empty] | Cut 0.1 Delivered to AMZ |  | EXEC CUT | [5 empty] | DIRECTOR CUT |  | 2022-06-03
2001-07-21 | [17 empty] | 2022-06-04
2001-07-22 | [17 empty] | 2022-06-05
2001-07-23 |  |  |  |  | 4 | PRELOCK VFX TO | 1 | AMAZON CUTS (4 WEEKS) |  | EXEC CUT | [5 empty] | DIRECTOR CUT |  | 2022-06-06 |  | JJ | AS | 4 | 4 | 4 |  | 4 | 4 | 4 |  |  |  | 23
2001-07-24 | [9 empty] | EXEC CUT | [5 empty] | DIRECTOR CUT |  | 2022-06-07
2001-07-25 | [9 empty] | EXEC CUT | [5 empty] | DIRECTOR CUT |  | 2022-06-08
2001-07-26 | [5 empty] | Cut 2 delivered to AMZ EOD |  | Cut 0.2 Delivered to AMZ EOD |  | EXEC CUT | [5 empty] | DIRECTOR CUT |  | 2022-06-09
2001-07-27 | [9 empty] | Cut 0.1 Delivered to AMZ | [5 empty] | Ep 6 Directors Cut delivered to Producers |  | 2022-06-10
2001-07-28 | [17 empty] | 2022-06-11
2001-07-29 | [17 empty] | 2022-06-12
2001-07-30 |  |  |  |  | 5 |  | 2 |  |  | AMAZON CUTS (4 WEEKS) |  | EXEC CUT | [5 empty] | 2022-06-13 |  | JJ | AS | 5 | 5 | 5 |  | 5 | 5 | 5 |  | 1st |  | 24
2001-07-31 | [11 empty] | EXEC CUT | [5 empty] | 2022-06-14
2001-08-01 | [5 empty] | Cut 3 delivered to AMZ EOD |  | Cut 1 Delivered to AMZ EOD |  |  |  | EXEC CUT | [5 empty] | 2022-06-15
2001-08-02 | [9 empty] | Cut 0.2 Delivered to AMZ EOD |  | EXEC CUT | [5 empty] | 2022-06-16
2001-08-03 | [11 empty] | EXEC CUT | [5 empty] | 2022-06-17
2001-08-04 | [17 empty] | 2022-06-18
2001-08-05 | [17 empty] | 2022-06-19
2001-08-06 |  |  |  |  | 6 | LOCKED TIMING CUT - PICTURE LOCK | 0 | PRELOCK VFX TO | 1 |  |  | EXEC CUT | [5 empty] | 2022-06-20 |  | JJ | AS | 6 | 6 | 6 |  | 6 | 6 | 6 |  |  |  | 25
2001-08-07 | [5 empty] | TO / VFX PULLS / VFX STARTS | [5 empty] | EXEC CUT | [5 empty] | 2022-06-21
2001-08-08 | [9 empty] | Cut 1 Delivered to AMZ EOD |  | EXEC CUT | [5 empty] | 2022-06-22
2001-08-09 | [7 empty] | Cut 2 delivered to AMZ EOD |  |  |  | EXEC CUT | [5 empty] | 2022-06-23
2001-08-10 | [11 empty] | Cut 0.1 Delivered to AMZ | [5 empty] | 2022-06-24
2001-08-11 | [17 empty] | 2022-06-25
2001-08-12 | [17 empty] | 2022-06-26
2001-08-13 |  |  |  |  | 7 |  | 1 |  | 2 | PRELOCK VFX TO | 1 | AMAZON CUTS (4 WEEKS) | [5 empty] | 2022-06-27 |  | JJ | AS | 7 | 7 | 7 |  | 7 | 7 | 7 |  |  |  | 26
2001-08-14 | Good omens moving to London? | [16 empty] | 2022-06-28
2001-08-15 | [7 empty] | Cut 3 delivered to AMZ EOD | [9 empty] | 2022-06-29
2001-08-16 | [9 empty] | Cut 2 delivered to AMZ EOD |  | Cut 0.2 Delivered to AMZ EOD | [5 empty] | 2022-06-30
2001-08-17 | [17 empty] | 2022-07-01
2001-08-18 | [17 empty] | 2022-07-02
2001-08-19 | [17 empty] | 2022-07-03
2001-08-20 |  |  |  |  | 8 | CONFORM | 2 | LOCKED TIMING CUT - PICTURE LOCK | 0 |  | 2 | [6 empty] | 2022-07-04 |  | JJ | AS | 8 | 8 | 8 |  | 8 | 8 | 8 |  |  |  | 27
2001-08-21 | [5 empty] | CONFORM |  | TO / VFX PULLS / VFX STARTS | [9 empty] | 2022-07-05
2001-08-22 | [5 empty] | PRE-GRADE ONLINE SPOTTING SESSION |  |  |  | Cut 3 delivered to AMZ EOD |  | Cut 1 Delivered to AMZ EOD | [5 empty] | 2022-07-06
2001-08-23 | [5 empty] | PRE-GRADE ONLINE |  | CONFORM | [9 empty] | 2022-07-07
2001-08-24 | [5 empty] | PRE-GRADE ONLINE |  | CONFORM | [9 empty] | 2022-07-08
2001-08-25 | [17 empty] | 2022-07-09
2001-08-26 | [17 empty] | 2022-07-10
2001-08-27 |  |  |  |  | 9 | GRADE 1st PASS (D1) | 3 | PRE-GRADE ONLINE SPOTTING SESSION | 1 | LOCKED TIMING CUT - PICTURE LOCK | 0 | PRELOCK VFX TO | 1 | EXEC CUT |  |  |  | 2022-07-11 |  | JJ | AS | 9 | 9 | 9 |  | 9 | 9 | 9 |  | 1st |  | 28
2001-08-28 | [5 empty] | GRADE 1st PASS (D2) |  | PRE-GRADE ONLINE |  | TO / VFX PULLS / VFX STARTS |  |  |  | EXEC CUT |  |  |  | 2022-07-12
2001-08-29 | [5 empty] | GRADE OVERRUN |  | PRE-GRADE ONLINE | [5 empty] | EXEC CUT |  |  |  | 2022-07-13
2001-08-30 | [7 empty] | GRADE 1st PASS (D1) |  |  |  | Cut 2 delivered to AMZ EOD |  | EXEC CUT |  |  |  | 2022-07-14
2001-08-31 | [7 empty] | GRADE 1st PASS (D2) | [5 empty] | EXEC CUT |  |  |  | 2022-07-15
2001-09-01 | [17 empty] | 2022-07-16
2001-09-02 | [17 empty] | 2022-07-17
2001-09-03 |  |  |  |  | 10 |  | 4 |  | 2 | CONFORM | 1 |  | 2 | EXEC CUT |  |  |  | 2022-07-18 |  | JJ | AS | 10 | 10 | 10 |  | 10 | 10 | 10 |  |  |  | 29
2001-09-04 | [9 empty] | CONFORM |  |  |  | EXEC CUT |  |  |  | 2022-07-19
2001-09-05 | [9 empty] | PRE-GRADE ONLINE SPOTTING SESSION |  | Cut 3 delivered to AMZ EOD |  | EXEC CUT |  |  |  | 2022-07-20
2001-09-06 | [13 empty] | EXEC CUT |  |  |  | 2022-07-21
2001-09-07 | [13 empty] | Cut 0.1 Delivered to AMZ |  |  |  | 2022-07-22
2001-09-08 | [17 empty] | 2022-07-23
2001-09-09 | [17 empty] | 2022-07-24
2001-09-10 |  |  |  |  | 11 |  | 5 |  | 3 | PRE-GRADE ONLINE | 2 | LOCKED TIMING CUT - PICTURE LOCK | 0 | AMAZON CUTS (4 WEEKS) |  | EXEC CUT |  | 2022-07-25 |  | JJ | AS |  | 11 | 11 |  | 11 | 11 | 11 |  |  |  | 30
2001-09-11 | [9 empty] | PRE-GRADE ONLINE |  | TO / VFX PULLS / VFX STARTS |  |  |  | EXEC CUT |  | 2022-07-26
2001-09-12 | [9 empty] | PRE-GRADE ONLINE | [5 empty] | EXEC CUT |  | 2022-07-27
2001-09-13 | [13 empty] | Cut 0.2 Delivered to AMZ EOD |  | EXEC CUT |  | 2022-07-28
2001-09-14 | [15 empty] | EXEC CUT |  | 2022-07-29
2001-09-15 | [17 empty] | 2022-07-30
2001-09-16 | [17 empty] | 2022-07-31
2001-09-17 |  |  |  |  | 12 |  | 6 |  | 4 |  | 3 | CONFORM | 1 |  |  | EXEC CUT |  | 2022-08-01 |  | JJ | AS |  | 12 | 12 |  | 12 | 12 | 12 |  |  |  | 31
2001-09-18 | [11 empty] | CONFORM |  |  |  | EXEC CUT |  | 2022-08-02
2001-09-19 | [13 empty] | Cut 1 Delivered to AMZ EOD |  | EXEC CUT |  | 2022-08-03
2001-09-20 | [15 empty] | EXEC CUT |  | 2022-08-04
2001-09-21 | [15 empty] | Cut 0.1 Delivered to AMZ |  | 2022-08-05
2001-09-22 | [17 empty] | 2022-08-06
2001-09-23 | [17 empty] | 2022-08-07
2001-09-24 |  |  |  |  | 13 | SCORE RECORD | 7 |  | 6 |  | 4 | PRE-GRADE ONLINE SPOTTING SESSION | 2 | PRELOCK VFX TO | 1 | AMAZON CUTS (4 WEEKS) |  | 2022-08-08 |  | JJ | AS |  | 13 | 13 |  | 13 | 13 | 13 |  | 2nd |  | 32
2001-09-25 | [5 empty] | SCORE RECORD | [5 empty] | PRE-GRADE ONLINE | [5 empty] | 2022-08-09
2001-09-26 | [5 empty] | SCORE RECORD | [5 empty] | PRE-GRADE ONLINE | [5 empty] | 2022-08-10
2001-09-27 | [5 empty] | SCORE RECORD | [7 empty] | Cut 2 delivered to AMZ EOD |  | Cut 0.2 Delivered to AMZ EOD |  | 2022-08-11
2001-09-28 | [5 empty] | SCORE RECORD | [11 empty] | 2022-08-12
2001-09-29 | [17 empty] | 2022-08-13
2001-09-30 | [17 empty] | 2022-08-14
2001-10-01 |  |  |  |  | 14 | MUSIC MIX | 8 |  | 7 |  | 6 |  | 3 |  | 2 |  |  | 2022-08-15 |  | JJ | AS |  | 14 | 14 |  | 14 | 14 | 14 |  |  |  | 33
2001-10-02 | [5 empty] | MUSIC MIX | [11 empty] | 2022-08-16
2001-10-03 | [5 empty] | MUSIC MIX | [7 empty] | Cut 3 delivered to AMZ EOD |  | Cut 1 Delivered to AMZ EOD |  | 2022-08-17
2001-10-04 | [5 empty] | MUSIC MIX | [11 empty] | 2022-08-18
2001-10-05 | [5 empty] | MUSIC DELIVER | [11 empty] | 2022-08-19
2001-10-06 | [17 empty] | 2022-08-20
2001-10-07 | [17 empty] | 2022-08-21
2001-10-08 |  |  |  |  | 15 |  | 9 |  | 8 | GRADE 1st PASS (D1) | 7 |  | 4 | LOCKED TIMING CUT - PICTURE LOCK | 0 | PRELOCK VFX TO | 1 | 2022-08-22 |  | JJ | AS |  | 15 | 15 |  | 15 | 15 | 15 |  | 1st |  | 34
2001-10-09 | [9 empty] | GRADE 1st PASS (D2) |  |  |  | TO / VFX PULLS / VFX STARTS |  |  |  | 2022-08-23 | [11 empty] | 1st
2001-10-10 | [17 empty] | 2022-08-24 | [11 empty] | 1st
2001-10-11 | [11 empty] | GRADE 1st PASS (D1) |  |  |  | Cut 2 delivered to AMZ EOD |  | 2022-08-25 | [11 empty] | 1st
2001-10-12 | [11 empty] | GRADE 1st PASS (D2) | [5 empty] | 2022-08-26 | [11 empty] | 1st
2001-10-13 | [17 empty] | 2022-08-27
2001-10-14 | [17 empty] | 2022-08-28
2001-10-15 |  |  |  |  | 16 |  | 10 | SCORE RECORD | 9 |  | 8 |  | 6 | CONFORM | 1 |  | 2 | 2022-08-29 |  |  | AS |  | 16 | 16 |  | 16 | 16 | 16 |  | 1st |  | 35
2001-10-16 | [5 empty] | AMAZON VFX + PICTURE REVIEW + MUSIC |  | SCORE RECORD | [5 empty] | CONFORM |  |  |  | 2022-08-30 | [11 empty] | 1st
2001-10-17 | [7 empty] | SCORE RECORD | [7 empty] | Cut 3 delivered to AMZ EOD |  | 2022-08-31 | [11 empty] | 1st
2001-10-18 | [7 empty] | SCORE RECORD | [9 empty] | 2022-09-01 | [11 empty] | 1st
2001-10-19 | [7 empty] | SCORE RECORD | [9 empty] | 2022-09-02 | [11 empty] | 1st
2001-10-20 | [17 empty] | 2022-09-03
2001-10-21 | [17 empty] | 2022-09-04
2001-10-22 |  |  |  |  | 17 | ADR | 11 | MUSIC MIX | 10 | ADR | 9 |  | 7 | PRE-GRADE ONLINE SPOTTING SESSION | 2 | LOCKED TIMING CUT - PICTURE LOCK | 0 | 2022-09-05 |  |  | AS |  |  | 17 |  | 17 | 17 | 17 |  |  |  | 36
2001-10-23 | [5 empty] | ADR |  | MUSIC MIX |  | ADR |  |  |  | PRE-GRADE ONLINE |  | TO / VFX PULLS / VFX STARTS |  | 2022-09-06
2001-10-24 | [5 empty] | ADR |  | MUSIC MIX |  | ADR |  |  |  | PRE-GRADE ONLINE |  |  |  | 2022-09-07
2001-10-25 | [5 empty] | ADR |  | MUSIC MIX |  | ADR | [7 empty] | 2022-09-08
2001-10-26 | [5 empty] | ADR |  | MUSIC DELIVER |  | ADR | [7 empty] | 2022-09-09
2001-10-27 | [17 empty] | 2022-09-10
2001-10-28 | [17 empty] | 2022-09-11
2001-10-29 |  |  |  |  | 18 | ADR | 12 |  | 11 | ADR | 10 |  | 8 |  | 3 | CONFORM | 1 | 2022-09-12 |  |  | AS |  |  | 18 |  | 18 | 18 | 18 |  |  |  | 37
2001-10-30 | [5 empty] | ADR |  |  |  | ADR | [5 empty] | CONFORM |  | 2022-09-13
2001-10-31 | [5 empty] | ADR |  |  |  | ADR | [5 empty] | PRE-GRADE ONLINE SPOTTING SESSION |  | 2022-09-14
2001-11-01 | [5 empty] | ADR |  |  |  | ADR | [5 empty] | PRE-GRADE ONLINE |  | 2022-09-15
2001-11-02 | [5 empty] | ADR |  |  |  | ADR | [5 empty] | PRE-GRADE ONLINE |  | 2022-09-16
2001-11-03 | [17 empty] | 2022-09-17
2001-11-04 | [17 empty] | 2022-09-18
2001-11-05 |  |  |  |  | 19 | ADR | 13 |  | 12 | ADR | 11 |  | 9 | GRADE 1st PASS (D1) | 4 |  | 2 | 2022-09-19 |  |  | AS |  |  | 19 |  | 19 | 19 | 19 |  | 1st | SH 1st | 38
2001-11-06 | [5 empty] | ADR |  |  |  | ADR |  |  |  | GRADE 1st PASS (D2) |  |  |  | 2022-09-20 | [11 empty] | 1st
2001-11-07 | [5 empty] | ADR |  |  |  | ADR | [7 empty] | 2022-09-21 | [11 empty] | 1st
2001-11-08 | [5 empty] | ADR |  |  |  | ADR | [7 empty] | 2022-09-22 | [11 empty] | 1st
2001-11-09 | [5 empty] | ADR |  |  |  | ADR | [7 empty] | 2022-09-23 | [11 empty] | 1st
2001-11-10 | [17 empty] | 2022-09-24
2001-11-11 | [17 empty] | 2022-09-25
2001-11-12 |  |  |  |  | 20 |  | 14 |  | 13 |  | 12 |  | 10 |  | 6 | GRADE 1st PASS (D1) | 3 | 2022-09-26 |  |  | AS |  |  | 20 |  | 20 | 20 | 20 |  | 1st |  | 39
2001-11-13 | [15 empty] | GRADE 1st PASS (D2) |  | 2022-09-27 | [11 empty] | 1st
2001-11-14 | [17 empty] | 2022-09-28 | [11 empty] | 1st
2001-11-15 | [17 empty] | 2022-09-29 | [11 empty] | 1st
2001-11-16 | [17 empty] | 2022-09-30 | [11 empty] | 1st
2001-11-17 | [17 empty] | 2022-10-01
2001-11-18 | [17 empty] | 2022-10-02
2001-11-19 |  |  |  |  | 21 |  | 15 |  | 14 | SCORE RECORD | 13 |  | 11 |  | 7 |  | 4 | 2022-10-03 | [7 empty] | 21 |  | 21 |  | 1st |  | 40
2001-11-20 | [7 empty] | AMAZON VFX + PICTURE REVIEW |  | SCORE RECORD | [7 empty] | 2022-10-04 | [11 empty] | 1st
2001-11-21 | [9 empty] | SCORE RECORD | [7 empty] | 2022-10-05 | [11 empty] | 1st
2001-11-22 | [9 empty] | SCORE RECORD | [7 empty] | 2022-10-06 | [11 empty] | 1st
2001-11-23 | [9 empty] | SCORE RECORD | [7 empty] | 2022-10-07 | [11 empty] | 1st
2001-11-24 | [17 empty] | 2022-10-08
2001-11-25 | [17 empty] | 2022-10-09
2001-11-26 |  |  |  |  | 22 |  | 16 |  | 15 | MUSIC MIX | 14 |  | 12 |  | 8 |  | 6 | 2022-10-10 | [7 empty] | 22 |  | 22 |  | ?? |  | 41
2001-11-27 | [9 empty] | MUSIC MIX | [7 empty] | 2022-10-11
2001-11-28 | [9 empty] | MUSIC MIX | [7 empty] | 2022-10-12
2001-11-29 | [9 empty] | MUSIC MIX | [7 empty] | 2022-10-13
2001-11-30 | [9 empty] | MUSIC DELIVER | [7 empty] | 2022-10-14
2001-12-01 | [17 empty] | 2022-10-15
2001-12-02 | [17 empty] | 2022-10-16
2001-12-03 |  |  |  |  | 23 |  | 17 | ADR | 16 |  | 15 |  | 13 | ADR | 9 |  | 7 | 2022-10-17 | [7 empty] | 23 |  | 23 |  |  |  | 42
2001-12-04 | [7 empty] | ADR | [5 empty] | ADR |  |  |  | 2022-10-18
2001-12-05 | [7 empty] | ADR | [5 empty] | ADR |  |  |  | 2022-10-19
2001-12-06 | [7 empty] | ADR | [5 empty] | ADR |  |  |  | 2022-10-20
2001-12-07 | [7 empty] | ADR | [5 empty] | ADR |  |  |  | 2022-10-21
2001-12-08 | [17 empty] | 2022-10-22
2001-12-09 | [17 empty] | 2022-10-23
2001-12-10 |  |  |  |  | 24 |  | 18 | ADR | 17 |  | 16 | SCORE RECORD | 14 | ADR | 10 |  | 8 | 2022-10-24 | [7 empty] | 24 |  | 24 |  | 1st |  | 43
2001-12-11 | [7 empty] | ADR |  | AMAZON VFX + PICTURE REVIEW |  | SCORE RECORD |  | ADR |  |  |  | 2022-10-25
2001-12-12 | [7 empty] | ADR |  |  |  | SCORE RECORD |  | ADR |  |  |  | 2022-10-26
2001-12-13 | [7 empty] | ADR |  |  |  | SCORE RECORD |  | ADR |  |  |  | 2022-10-27
2001-12-14 | [7 empty] | ADR |  |  |  | SCORE RECORD |  | ADR |  |  |  | 2022-10-28
2001-12-15 | [17 empty] | 2022-10-29
2001-12-16 | [17 empty] | 2022-10-30
2001-12-17 |  |  |  |  | 25 |  | 19 | ADR | 18 |  | 17 | MUSIC MIX | 15 | ADR | 11 |  | 9 | 2022-10-31 | [7 empty] | 25 |  | 25 |  |  | SH 1st | 44
2001-12-18 | [7 empty] | ADR |  |  |  | MUSIC MIX |  | ADR |  |  |  | 2022-11-01
2001-12-19 | [7 empty] | ADR |  |  |  | MUSIC MIX |  | ADR |  |  |  | 2022-11-02
2001-12-20 | [7 empty] | ADR |  |  |  | MUSIC MIX |  | ADR |  |  |  | 2022-11-03
2001-12-21 | [5 empty] | VFX DELIVER |  | ADR |  |  |  | MUSIC DELIVER |  | ADR |  |  |  | 2022-11-04
2001-12-22 | [17 empty] | 2022-11-05
2001-12-23 | [17 empty] | 2022-11-06
2001-12-24 |  |  |  |  | 26 | FINAL GRADE |  |  | 19 |  | 18 |  | 16 |  | 12 |  | 10 | 2022-11-07 | [7 empty] | 26 |  | 26 |  | 1st |  | 45
2001-12-25 | [5 empty] | FINAL GRADE | [5 empty] | AMAZON VFX + PICTURE REVIEW | [5 empty] | 2022-11-08
2001-12-26 | [5 empty] | FINAL GRADE | [11 empty] | 2022-11-09
2001-12-27 | [5 empty] | FINAL TITLING | [11 empty] | 2022-11-10
2001-12-28 | [5 empty] | DUBBING GUIDE | [11 empty] | 2022-11-11
2001-12-29 | [17 empty] | 2022-11-12
2001-12-30 | [17 empty] | 2022-11-13
2001-12-31 |  |  |  |  | 27 | FOLEY RECORD + FIT |  |  | 20 |  | 19 | ADR | 17 |  | 13 | ADR | 11 | 2022-11-14 | [7 empty] | 27 |  | 27 |  |  |  | 46
2002-01-01 | [5 empty] | FOLEY RECORD + FIT | [5 empty] | ADR |  |  |  | ADR |  | 2022-11-15
2002-01-02 | [5 empty] | FOLEY RECORD + FIT | [5 empty] | ADR |  |  |  | ADR |  | 2022-11-16
2002-01-03 | [11 empty] | ADR |  |  |  | ADR |  | 2022-11-17
2002-01-04 | [7 empty] | VFX DELIVER |  |  |  | ADR |  |  |  | ADR |  | 2022-11-18
2002-01-05 | [17 empty] | 2022-11-19
2002-01-06 | [17 empty] | 2022-11-20
2002-01-07 |  |  |  |  | 28 | PRE-MIX |  | FOLEY RECORD + FIT |  |  | 20 | ADR | 18 |  | 14 | ADR | 12 | 2022-11-21 | [7 empty] | 28 |  | 28 |  |  |  | 47
2002-01-08 | [5 empty] | PRE-MIX |  | FOLEY RECORD + FIT |  |  |  | ADR |  |  |  | ADR |  | 2022-11-22
2002-01-09 | [5 empty] | PRE-MIX |  | FOLEY RECORD + FIT |  |  |  | ADR |  |  |  | ADR |  | 2022-11-23
2002-01-10 | [5 empty] | PRE-MIX | [5 empty] | ADR |  |  |  | ADR |  | 2022-11-24
2002-01-11 | [5 empty] | FINAL MIX | [5 empty] | ADR |  |  |  | ADR |  | 2022-11-25
2002-01-12 | [17 empty] | 2022-11-26
2002-01-13 | [17 empty] | 2022-11-27
2002-01-14 |  |  |  |  | 29 | FINAL MIX |  | FINAL GRADE |  |  | 21 | ADR | 19 | SCORE RECORD | 15 | ADR | 13 | 2022-11-28 | [7 empty] | 29 |  | 29 |  | 1st | SH 1st | 48
2002-01-15 | [5 empty] | FINAL MIX REVIEW |  | FINAL GRADE |  |  |  | ADR |  | SCORE RECORD |  | ADR |  | 2022-11-29
2002-01-16 | [5 empty] | 5.1 M&E |  | FINAL GRADE |  |  |  | ADR |  | SCORE RECORD |  | ADR |  | 2022-11-30
2002-01-17 | [5 empty] | DELIVERY MIXES |  | FINAL TITLING |  |  |  | ADR |  | SCORE RECORD |  | ADR |  | 2022-12-01
2002-01-18 | [5 empty] | DOLBY ATMOS REMIX |  | DUBBING GUIDE |  | VFX DELIVER |  | ADR |  | SCORE RECORD |  | ADR |  | 2022-12-02
2002-01-19 | [17 empty] | 2022-12-03
2002-01-20 | [17 empty] | 2022-12-04
2002-01-21 |  |  |  |  | 30 | DOLBY ATMOS REMIX M&E |  | PRE-MIX |  | FOLEY RECORD + FIT |  |  | 20 | MUSIC MIX | 16 |  | 14 | 2022-12-05 | [7 empty] | 30 |  | 30 |  |  |  | 49
2002-01-22 | [5 empty] | FINAL ONLINE REVIEW |  | PRE-MIX |  | FOLEY RECORD + FIT |  |  |  | MUSIC MIX |  |  |  | 2022-12-06
2002-01-23 | [5 empty] | FINAL ONLINE OVERRUN |  | PRE-MIX |  | FOLEY RECORD + FIT |  |  |  | MUSIC MIX |  |  |  | 2022-12-07
2002-01-24 | [5 empty] | RENDER HDR |  | PRE-MIX | [5 empty] | MUSIC MIX |  |  |  | 2022-12-08
2002-01-25 | [5 empty] | RENDER HDR |  | FINAL MIX | [5 empty] | MUSIC DELIVER |  |  |  | 2022-12-09
2002-01-26 | [17 empty] | 2022-12-10
2002-01-27 | [17 empty] | 2022-12-11
2002-01-28 |  |  |  |  | 31 | RENDER HDR |  | FINAL MIX |  | FINAL GRADE |  |  | 21 |  | 17 |  | 15 | 2022-12-12 | [7 empty] | 31 |  | 31 |  | 1st | FN 1st / SH 2nd | 50
2002-01-29 | [5 empty] | HDR QC |  | FINAL MIX REVIEW |  | FINAL GRADE |  |  |  | AMAZON VFX + PICTURE REVIEW |  | AMAZON VFX + PICTURE REVIEW |  | 2022-12-13
2002-01-30 | [5 empty] | HDR QC |  | 5.1 M&E |  | FINAL GRADE | [7 empty] | 2022-12-14
2002-01-31 | [5 empty] | HDR QC |  | DELIVERY MIXES |  | FINAL TITLING | [7 empty] | 2022-12-15
2002-02-01 | [5 empty] | 101 DELIVER to VDMS |  | DOLBY ATMOS REMIX |  | DUBBING GUIDE |  | VFX DELIVER | [5 empty] | 2022-12-16
2002-02-02 | [17 empty] | 2022-12-17
2002-02-03 | [17 empty] | 2022-12-18
2002-02-04 | CHRISTMAS HIATUS | [16 empty] | 2022-12-19 | [13 empty] | 51
2002-02-05 | [17 empty] | 2022-12-20
2002-02-06 | [17 empty] | 2022-12-21
2002-02-07 | [17 empty] | 2022-12-22
2002-02-08 | [17 empty] | 2022-12-23
2002-02-09 | [17 empty] | 2022-12-24
2002-02-10 | [17 empty] | 2022-12-25
2002-02-11 | [17 empty] | 2022-12-26 | [13 empty] | 52
2002-02-12 | CHRISTMAS HIATUS | [16 empty] | 2022-12-27
2002-02-13 | [17 empty] | 2022-12-28
2002-02-14 | [17 empty] | 2022-12-29
2002-02-15 | [17 empty] | 2022-12-30
2002-02-16 | [17 empty] | 2022-12-31
2002-02-17 | [17 empty] | 2023-01-01
2002-02-18 |  |  |  |  | 32 | VDMS QC |  | DOLBY ATMOS REMIX M&E |  | PRE-MIX |  | FINAL GRADE |  |  | 18 |  | 16 | 2023-01-02 | [7 empty] | 32 |  | 32 |  | 1st |  | 53
2002-02-19 | [5 empty] | VDMS QC |  | FINAL ONLINE REVIEW |  | PRE-MIX |  | FINAL GRADE | [5 empty] | 2023-01-03
2002-02-20 | [5 empty] | VDMS QC |  | FINAL ONLINE OVERRUN |  | PRE-MIX |  | FINAL GRADE | [5 empty] | 2023-01-04
2002-02-21 | [5 empty] | VDMS QC |  | RENDER HDR |  | PRE-MIX |  | FINAL TITLING | [5 empty] | 2023-01-05
2002-02-22 | [5 empty] | VDMS QC HDR PASS |  | RENDER HDR |  | FINAL MIX |  | DUBBING GUIDE | [5 empty] | 2023-01-06
2002-02-23 | [17 empty] | 2023-01-07
2002-02-24 | [17 empty] | 2023-01-08
2002-02-25 |  |  |  |  | 33 | VDMS QC |  | RENDER HDR |  | FINAL MIX |  | FOLEY RECORD + FIT |  |  | 19 | SCORE RECORD | 17 | 2023-01-09 | [7 empty] | 33 |  | 33 |  | 1st | FN 1st / SH 2nd | 54
2002-02-26 | [5 empty] | VDMS QC |  | HDR QC |  | FINAL MIX REVIEW |  | FOLEY RECORD + FIT |  |  |  | SCORE RECORD |  | 2023-01-10
2002-02-27 | [5 empty] | VDMS QC |  | HDR QC |  | 5.1 M&E |  | FOLEY RECORD + FIT |  |  |  | SCORE RECORD |  | 2023-01-11
2002-02-28 | [5 empty] | VDMS QC |  | HDR QC |  | DELIVERY MIXES | [5 empty] | SCORE RECORD |  | 2023-01-12
2002-03-01 | [5 empty] | VDMS QC SDR PASS |  | 101 DELIVER to VDMS |  | DOLBY ATMOS REMIX | [5 empty] | SCORE RECORD |  | 2023-01-13
2002-03-02 | [17 empty] | 2023-01-14
2002-03-03 | [17 empty] | 2023-01-15
2002-03-04 |  |  |  |  | 34 | CC / AD |  | VDMS QC |  | DOLBY ATMOS REMIX M&E |  |  |  | FOLEY RECORD + FIT | 20 | MUSIC MIX | 18 | 2023-01-16 | [7 empty] | 34 |  | 34 |  |  | FN 1st / SH 2nd | 55
2002-03-05 | [5 empty] | CC / AD |  | VDMS QC |  | FINAL ONLINE REVIEW |  | PRE-MIX |  | FOLEY RECORD + FIT |  | MUSIC MIX |  | 2023-01-17
2002-03-06 | [5 empty] | CC / AD |  | VDMS QC |  | FINAL ONLINE OVERRUN |  | PRE-MIX |  | FOLEY RECORD + FIT |  | MUSIC MIX |  | 2023-01-18
2002-03-07 | [5 empty] | CC / AD |  | VDMS QC |  | RENDER HDR |  | PRE-MIX |  |  |  | MUSIC MIX |  | 2023-01-19
2002-03-08 | [5 empty] | FINALISE CC / AD |  | VDMS QC HDR PASS |  | RENDER HDR |  | PRE-MIX |  |  |  | MUSIC DELIVER |  | 2023-01-20
2002-03-09 | [17 empty] | 2023-01-21
2002-03-10 | [17 empty] | 2023-01-22
2002-03-11 |  |  |  |  | 35 |  |  | VDMS QC |  | RENDER HDR |  |  |  | PRE-MIX | 21 |  | 19 | 2023-01-23 | [7 empty] | 35 |  | 35 |  |  |  | 56
2002-03-12 | [7 empty] | VDMS QC |  | HDR QC |  |  |  | PRE-MIX |  |  |  | 2023-01-24
2002-03-13 | [7 empty] | VDMS QC |  | HDR QC |  |  |  | PRE-MIX |  |  |  | 2023-01-25
2002-03-14 | [7 empty] | VDMS QC |  | HDR QC |  |  |  | PRE-MIX |  |  |  | 2023-01-26
2002-03-15 | [5 empty] | DELIVERY TO AMAZON COMPLETE |  | VDMS QC SDR PASS |  | 101 DELIVER to VDMS |  |  |  | VFX DELIVER |  |  |  | 2023-01-27
2002-03-16 | [17 empty] | 2023-01-28
2002-03-17 | [17 empty] | 2023-01-29
2002-03-18 |  |  |  |  | 36 |  |  | CC / AD |  | VDMS QC |  | FINAL MIX |  | FINAL GRADE |  | FOLEY RECORD + FIT | 20 | 2023-01-30 | [7 empty] | 36 |  | 36 |  | 1st | FN 1st / SH 2nd | 57
2002-03-19 | [7 empty] | CC / AD |  | VDMS QC |  | FINAL MIX |  | FINAL GRADE |  | FOLEY RECORD + FIT |  | 2023-01-31
2002-03-20 | [7 empty] | CC / AD |  | VDMS QC |  | FINAL MIX |  | FINAL GRADE |  | FOLEY RECORD + FIT |  | 2023-02-01
2002-03-21 | [7 empty] | CC / AD |  | VDMS QC |  | 5.1 M&E |  | FINAL TITLING |  |  |  | 2023-02-02
2002-03-22 | [7 empty] | FINALISE CC / AD |  | VDMS QC HDR PASS |  | DELIVERY MIXES |  | DUBBING GUIDE |  | VFX DELIVER |  | 2023-02-03
2002-03-23 | [17 empty] | 2023-02-04
2002-03-24 | [17 empty] | 2023-02-05
2002-03-25 |  |  |  |  | 37 |  |  |  |  | VDMS QC |  | DOLBY ATMOS REMIX |  | FINAL MIX |  | FINAL GRADE |  | 2023-02-06 | [7 empty] | 37 |  | 37 |  | 1st | SH 1st | 58
2002-03-26 | [9 empty] | VDMS QC |  | DOLBY ATMOS REMIX M&E |  | FINAL MIX |  | FINAL GRADE |  | 2023-02-07
2002-03-27 | [9 empty] | VDMS QC |  | FINAL ONLINE REVIEW |  | FINAL MIX |  | FINAL GRADE |  | 2023-02-08
2002-03-28 | [9 empty] | VDMS QC |  | FINAL ONLINE OVERRUN |  | 5.1 M&E |  | FINAL TITLING |  | 2023-02-09
2002-03-29 | [7 empty] | DELIVERY TO AMAZON COMPLETE |  | VDMS QC SDR PASS |  | RENDER HDR |  | DELIVERY MIXES |  | DUBBING GUIDE |  | 2023-02-10
2002-03-30 | [17 empty] | 2023-02-11
2002-03-31 | [17 empty] | 2023-02-12
2002-04-01 |  |  |  |  | 38 |  |  |  |  | CC / AD |  | RENDER HDR |  | FINAL ONLINE REVIEW |  | PRE-MIX |  | 2023-02-13 | [7 empty] | 38 |  | 38 |  |  |  | 59
2002-04-02 | [9 empty] | CC / AD |  | RENDER HDR |  | FINAL ONLINE OVERRUN |  | PRE-MIX |  | 2023-02-14
2002-04-03 | [9 empty] | CC / AD |  | HDR QC |  | RENDER HDR |  | PRE-MIX |  | 2023-02-15
2002-04-04 | [9 empty] | CC / AD |  | HDR QC |  | RENDER HDR |  | PRE-MIX |  | 2023-02-16
2002-04-05 | [9 empty] | FINALISE CC / AD |  | HDR QC |  | RENDER HDR |  | FINAL MIX |  | 2023-02-17
2002-04-06 | [17 empty] | 2023-02-18
2002-04-07 | [17 empty] | 2023-02-19
2002-04-08 |  |  |  |  | 39 | [6 empty] | VDMS QC |  | HDR QC |  | FINAL MIX |  | 2023-02-20 | [7 empty] | 39 |  |  |  |  | SH 1st | 60
2002-04-09 | [11 empty] | VDMS QC |  | HDR QC |  | FINAL MIX |  | 2023-02-21
2002-04-10 | [11 empty] | VDMS QC |  | HDR QC |  | FINAL MIX |  | 2023-02-22
2002-04-11 | [11 empty] | VDMS QC |  | HDR QC |  | DELIVERY MIX |  | 2023-02-23
2002-04-12 | [9 empty] | DELIVERY TO AMAZON COMPLETE |  | VDMS QC HDR PASS |  | 101 DELIVER to VDMS |  | DELIVERY MIX |  | 2023-02-24
2002-04-13 | [17 empty] | 2023-02-25
2002-04-14 | [17 empty] | 2023-02-26
2002-04-15 |  |  |  |  | 40 | [6 empty] | VDMS QC |  | VDMS QC |  | FINAL ONLINE REVIEW |  | 2023-02-27 | [7 empty] | 40
2002-04-16 | [11 empty] | VDMS QC |  | VDMS QC |  | FINAL ONLINE OVERRUN |  | 2023-02-28
2002-04-17 | [11 empty] | VDMS QC |  | VDMS QC |  | RENDER HDR |  | 2023-03-01
2002-04-18 | [11 empty] | VDMS QC |  | VDMS QC |  | RENDER HDR |  | 2023-03-02
2002-04-19 | [11 empty] | VDMS QC SDR PASS |  | VDMS QC HDR PASS |  | RENDER HDR |  | 2023-03-03
2002-04-20 | [17 empty] | 2023-03-04
2002-04-21 | [17 empty] | 2023-03-05
2002-04-22 |  |  |  |  | 41 | [6 empty] | CC / AD |  | VDMS QC |  | HDR QC |  | 2023-03-06 | [7 empty] | 41
2002-04-23 | [11 empty] | CC / AD |  | VDMS QC |  | HDR QC |  | 2023-03-07
2002-04-24 | [11 empty] | CC / AD |  | VDMS QC |  | HDR QC |  | 2023-03-08
2002-04-25 | [11 empty] | FINALISE CC / AD |  | VDMS QC |  | HDR QC |  | 2023-03-09
2002-04-26 | [11 empty] | DELIVERY TO AMAZON COMPLETE |  | VDMS QC SDR PASS |  | 101 DELIVER to VDMS |  | 2023-03-10
2002-04-27 | [17 empty] | 2023-03-11
2002-04-28 | [17 empty] | 2023-03-12
2002-04-29 |  |  |  |  | 42 | [8 empty] | CC / AD |  | VDMS QC |  | 2023-03-13 | [7 empty] | 42
2002-04-30 | [13 empty] | CC / AD |  | VDMS QC |  | 2023-03-14
2002-05-01 | [13 empty] | CC / AD |  | VDMS QC |  | 2023-03-15
2002-05-02 | [13 empty] | CC / AD |  | VDMS QC |  | 2023-03-16
2002-05-03 | [13 empty] | FINALISE CC / AD |  | VDMS QC HDR PASS |  | 2023-03-17
2002-05-04 | [17 empty] | 2023-03-18
2002-05-05 | [17 empty] | 2023-03-19
2002-05-06 |  |  |  |  | 43 | [10 empty] | VDMS QC |  | 2023-03-20
2002-05-07 | [15 empty] | VDMS QC |  | 2023-03-21
2002-05-08 | [15 empty] | VDMS QC |  | 2023-03-22
2002-05-09 | [15 empty] | VDMS QC |  | 2023-03-23
2002-05-10 | [13 empty] | DELIVERY TO AMAZON COMPLETE |  | VDMS QC SDR PASS |  | 2023-03-24
2002-05-11 | [17 empty] | 2023-03-25
2002-05-12 | [17 empty] | 2023-03-26
2002-05-13 |  |  |  |  | 44 | [10 empty] | CC / AD |  | 2023-03-27
2002-05-14 | [15 empty] | CC / AD |  | 2023-03-28
2002-05-15 | [15 empty] | CC / AD |  | 2023-03-29
2002-05-16 | [15 empty] | FINALISE CC / AD |  | 2023-03-30
2002-05-17 | POST WRAP & DELIVERY | [14 empty] | DELIVERY TO AMAZON COMPLETE |  | 2023-03-31
2002-05-18 | [17 empty] | 2023-04-01
2002-05-19 | [17 empty] | 2023-04-02
Note on AG35: Layla Blackman: Prep is short by 1 week at least
Note on AI35: Layla Blackman: Prep is short by 1 week at least
Note on AI36: Layla Blackman: Prep not budgeted.
Note on AG219: Layla Blackman: Need to add a week for cross over with London AE edit set up
Note on AE324: Layla Blackman: Week 16 not budgeted. This is needed for spotting sessions
Note on AF352: Layla Blackman: Week 20 not budgeted. Needed for spotting sessions.
Note on AH499: Layla Blackman: Potentially need AE on board in case of issues during final ep QC?